## Slide 1: Seminario Internacional: “Gestión Social de Metros en América Latina”
Lima - Perú
Agosto, 2016

## Slide 2: Risk Management in Underground Projects
By Leonardo Rosas Sánchez
D2 Consult International (Austria)

## Slide 3: Table of content
Introduction
Scope
Use of risk management
Objectives of risk management
Risk management in early design stages
Risk management during construction
Typical components of risk management
From risk management to monitoring (underground metro station Rotterdam)
Conclusions

## Slide 4: 1. Introduction

## Slide 5: Risks in tunneling
Tunneling and underground construction works impose risks on all parties involved (as well as on those not directly involved in the project):
  Due to the inherent uncertainties (ground and groundwater conditions) there might be significant cost overrun and delay risks as well as environmental risks
  There is a potential for large scale accidents during tunneling work
  For tunnels in urban areas, there is a risk of damage to a third party people and property (especially including heritage designated buildings)
  There is a risk that the problems which the tunneling project cause to the public will give rise to public protests affecting the course of the project

## Slide 6: Risk associated and risk management
Due to the inherent risk associated with underground construction works, risk management became an integral part of the most underground construction projects during the late 1990s:
  Establishing international guidelines on tunneling risk management
  ITA (International Tunneling Association) guidelines were completed in April 2003
Risk management processes can be significantly improved by using systematic risk management techniques throughout the tunnel project development
By the use of these techniques, potential problems can be clearly identified such that appropriate risk mitigation measures can be implemented in a timely manner

## Slide 7: 2. Scope

## Slide 8: Scope
The use of risk management from the early stages of a project (where major decisions such as choice of alignment and selection of construction methods can be influenced) is essential
The SCOPE of this presentation is to indicate to the owner what the tunneling industry recommends as the “best-practice” for risk management
“Risk Management” is the overall term which includes risk identification, risk assessment, risk analysis

## Slide 9: 3. Use of risk management

## Slide 10: Risk management and project development
Risk management may be used throughout the project from the early planning stage through to start of operation:
  Phase 1 - Design stage (feasibility and conceptual design)
  Phase 2 - Tendering and contract negotiation
  Phase 3 - Construction phase

## Slide 11: Phases of risk management
Phase 2 (Tendering and contract negotiation):
Requirement in tender documents
Risk assessment in tender evaluation
Risk clauses in contract
Phase 1 (Feasibility and conceptual design):
Establishing risk policy
Risk acceptance criteria
Qualitative risk assessment of the project
Detailed analysis of areas of special interest or concern
Phase 3 (construction phase):
Contractor’s risk management
Owner’s risk management
Joint risk management team between the owner and the contractor

## Slide 12: 4. Objectives of risk management

## Slide 13: Construction risk policy
The identification of risks resulting from design and construction is an early task early in an underground project
In order to form a common reference for all parties involved (owner, designers, insurers and contractors), a “construction risk policy” should be established by the OWNER
A construction risk policy for the project may indicate:
  Scope
  Risk objectives
  Risk management strategy

## Slide 14: Scope
The scope may include the following risk or consequences:
  Risk to the health and safety of workers, including personal injury and, in extreme, loss of life
  Risk to the health and safety of third parties
  Risk to third property, specifically existing buildings and structures, cultural heritage buildings and above and below ground infrastructure
  Risk to the environment including possible land, water or air pollution and damage to flora and fauna
  Risk to the owner in delay to the completion
  Risk to the owner in terms of financial losses and additional unplanned costs

## Slide 15: Risk objectives
The general objectives of the construction risk policy could be that proper risk management throughout the project will be ensured at all stages of the project by:
Identification of hazards
Identification of measures to eliminate or mitigate risks
Implementation of measures to eliminate or mitigate risks where economically feasible or required according to the specific risk objectives or health and safety legislation
Economically feasible may be defined using the ALARP principle (to reduce all risks covered to a level as low as reasonable practicable
Emphasis should be placed on minimizing overall risk by reducing the likelihood of occurrence of events with large consequences (significant political concern)
Allocation of risk between the parties: risks should be allocated to the party who has the best means for controlling the risk
Specific minimum risk objectives may be defined in addition to the general risk objectives:
For example, the general public should be exposed only to small additional risk from construction of the tunnel or underground works

## Slide 16: Risk management strategy
As part of the construction risk policy, a risk management strategy should be adopted
A recommended strategy is to carry out construction risk assessments at each stage of the design and construction in accordance with:
  Information available
  Decisions to be taken or revised at each stage
Any risk management strategy should include:
  A definition of the risk management responsibilities of the various parties involved (owner, consultant, contractor)
  A short description of the activities to be carried out at different stages of the project in order to achieve the objectives
  A scheme to be used for follow-up on results obtained through the risk management activities
  Identified hazards can be communicated to all parties
  Follow-up on initial assumptions regarding the operational phase
  Monitoring, audit and review procedures

## Slide 17: 5. Risk management in early design stages

## Slide 18: Effective risk management
For effective risk management of a tunneling project, it is vital that risk management is begun as early as possible (during the project feasibility and early planning stages)
The success and benefits of implementing effective risk management depends on:
  The quality of the identified risk mitigating actions
  The active involvement, experience and general opinion of the participants (owner, designers and contractors)

## Slide 19: First step in risk management
Establish risk policy
The primary step in establishing a risk management system is for the owner to formulate a risk policy
Risk management is not achieved by the enforcement of systems and procedures alone, but can be enhanced through seminars and meetings
  Understanding and appreciation of the risk management objectives are disseminated throughout the organizations
Risk acceptance criteria
The risk objectives expressed in general terms in the owner’s risk policy should be “translated” into risk acceptance criteria suitable for use in the risk assessment activities planned to be carried out:
  Risk acceptance criteria to be used in qualitative risk assessment
  Risk acceptance criteria to be used in quantitative risk assessments
A document should be provided that explains how the risk acceptance criteria are established in relation to the statements on risk objectives in the owner’s risk policy

## Slide 20: Qualitative risk assessment
During the early design stage, a qualitative risk assessment should be carried out focused on the identification of potential hazards:
  Construction activities expected to be included in the project
  Covering all types of risk noted in the construction risk policy
The main purposes of this work are:
  To raise the awareness of all concerned to the major risks involved in the construction
  To provide a structured basis for the design decisions to be taken in the early design stage
The qualitative risk assessment should include:
  Hazard identification
  Classification of the identified hazards
  Identification of risk mitigation measures
  Details of the risks in the project risk register indicating risk class and risk mitigation measures for each hazard

## Slide 21: Risk assessment Matrix
The identified hazards are classified according to the magnitude of the risk they represent:
  The purpose of this classification is to provide a framework for the decisions to be made on implementation of risk mitigation measures
Classification systems should be established covering frequencies and consequences as well as classification of risks on the basis of the frequency and consequence classes
The classification system may be included in the risk acceptance criteria

## Slide 22: Risk mitigation
Where risk levels conflict with the project’s risk acceptance criteria, it is mandatory to identify risk-reducing actions and provide documentation for the management decision on which actions are to be implemented
Risk mitigation at this phase of the project will primarily result in changes in technical solutions and possibly in alternative working procedures
Further, many risk-reducing actions can be decisions or statements to be written into the tender documents

## Slide 23: Risk management during preparation of tender documents
The following risk management activities should be carried out during preparation of the tender documents:
  Specification of technical and other requirements in the tender documents (risks are managed in accordance with the risk policy)
  The specification should detail responsibilities for risks in accordance with the general principles adopted for the project
  The qualitative risk assessment carried out in the early design stages should be repeated:
    Final modifications of the tender documents
    Document that risks has been managed in accordance with the risk policy
  Definition of the information requested from the tenderers in order to allow an evaluation of the tenderers’ ability to manage risk
  Specification of requirements concerning the contractor’s risk management activities during the execution of the contract

## Slide 24: Requirements to be specified in the tender documents
The tender documents should specify that the contractor must perform risk management in accordance with the owner’s risk policy
The contractor’s risk management system and approaches must be compatible with the owner’s (reducing and controlling risks to himself, to the owner and the public)
Requirements for the contractor’s risk management system may include:
  Organization and qualifications of risk management staff
  Types of risks to be considered and evaluated
  Minimum requirement of activities to be included in the contractor’s risk management
  Time schedule for risk management activities
  Coordination with other risk management teams (owner, other contractors, etc.)
  Control of risks from subcontractor’s activities

## Slide 25: Risk management during selection of contractor
The application of risk management techniques by the owner can be valuable in the selection of the successful tenderer
Identifying risk issues in the tenders can be used as a basis for tender negotiations
The evaluation of tenders in respect to risk may be qualitative (based on a points system) or on an quantitative basis (tender price might be adjusted accordingly)
The evaluation of the risks issues in the tenders should include:
  An evaluation of the contractor’s ability to identify and control risks by the choice and implementation of technical solutions
  Systematic assessment of the differences in risk between the project proposals by different tenders
  Evaluation of the risk management expertise at the contractor’s disposal

## Slide 26: Risk clauses in contract
When a contractor has been chosen, negotiations between the owner and the contractor may lead to a detailed contractual description of the risk management system to be implemented on the project:
  Intentions of the owner
  Suggested procedures of the contractor (improving cooperation between the parties)
Alternative technical solutions can also be negotiated on the basis of risk assessments carried out and stated in the contract
The risk assessment of the successful tender may have identified some previously undetected areas of risk
  Additional risk mitigation clauses may be introduced in the contract

## Slide 27: 6. Risk management during construction

## Slide 28
Early design stage
In the early design and tender and contract negotiation phases:
  Certain risks may be transferred (contractually or through insurance)
  Others may be retained
  Some risks can be eliminated and/or mitigated
Construction phase
Possibilities of risk transfer are minimal
The most advantageous strategy (for both the owner and contractor) is to reduce the severity of as many risks as possible:
  Risk elimination
  Risk mitigation

## Slide 29: Contractor’s risk management
Based on what has been agreed in the contract, the contractor’s responsibility includes:
  The fulfilment of the owner’s risk policy
  Establishing a carefully planned, well structures and easy-to-use risk management system
The contractor must identify hazards and classify risks using systems which are compatible with the system used by the owner and should propose mitigation measures to reduce the identified risks
Timely consideration and actions are of the essence in risk mitigation measures (anticipate and put in place effective proactive preventive measures)
Contingency and emergency plans must be devised, implemented and maintained throughout the entire project period to address foreseeable accidents and emergencies

## Slide 30: Owner’s risk management
It is recommended that the owner continues to perform risk assessment for risks that are the owner’s responsibility (and not covered by the contractor):
  Contractual risk (including contractual aspects of technical risks identified by the contractor)
  Risk related to economic loss to the owner, or delay
  Mitigation actions should be identified and implemented by the owner
  Some mitigation measures may be handed over to the contractor for implementation
The owner should encourage and monitor the contractor’s risk management:
  Quality control audits instituted by the owner
  To ensure that the contractor’s risk management system is properly implemented and functioning effectively

## Slide 31: 7. Typical components of risk management

## Slide 32: Hazard identification
General hazards
Contractual disputes
Insolvency and institutional problems
Authorities interference
Third party interference
Labor disputes
Specific hazards
Accidental occurrences
Unforeseen adverse conditions
Inadequate designs, specifications and programs
Failure of major equipment
Substandard, slow or out-of-tolerance works

## Slide 33: Classification
Frequency of occurrence and extent of consequences for each hazard should be assessed according to a classification system established specifically to suit the requirements and scale of the project
The classification of frequency, consequence and risk should be established in accordance with the risk objectives and risk acceptance criteria defined for the project
The frequency classification system should be common for all types of risk covered, whereas a consequence classification system must be established separately for each type of risk to be covered
An example of classification is outlined, using 5-fold classification systems

## Slide 34: Frequency classification
A separation of five classes or intervals is generally recommended as a practical way of classifying frequency
Frequency classification can be set up relating the number of events (hazards occurring) to a “per year” or “per km of tunnel” unit
However, it is proposed as the most suitable to use a classification that relates to the potential number of events during the whole construction period

## Slide 35: Consequence classification
It is recommended that consequences be classified into five classes or intervals
The selection of consequence types and potential severity will vary according to the scope and nature of the project
Guidelines and classification classes must be defined for each particular project in consideration of the specific risk policy
The following example:
  Underground construction project
  Project value about 1 billion Euro
  Duration: 5 – 7 years

## Slide 36: Risk classification and risk acceptance
An example of a risk matrix for the determination of risk levels is shown below
The risk classification system must be defined for each particular project in consideration of the specific risk policy

## Slide 37: 8. From risk management to monitoring

## Slide 38: Present Rotterdam Central Station
The present Rotterdam Central Station was opened in 1957 in the period of rebuilding after the World War II
However, the increasing pressure on public transport has resulted in the development of several mega projects in and around Rotterdam CS in the city center
The realization of a new metro line called RandstadRail demands the expansion and upgrading of the present underground metro station

## Slide 39: New metro station Rotterdam CS
The development of the new underground metro station distinguished itself by the very complex conditions under which the project has to be realized
The upgrading of the metro station is a key project which interferes with other big projects under construction or to be realized shortly at the same location
One of the prior conditions during all construction phases was to maintain full functionality of all services
  Metro station
  Train station
  Unobstructed operation of trams, buses and taxis

## Slide 40: Contractual requirements (Tendering and pre-construction phase)
The RET (Rotterdam public transport company) acting as client of the project and at the same time as operator of the metro station, commissioned RPW (Rotterdam Public Works)
The scope of works included:
  Technical design
  Risk management
  Preparation of tender documents including set up of detailed monitoring
The contractor is made responsible for all monitoring activities by making the monitoring specifications part of the contract:
  Contractor can and must directly monitor his work and the effects on surrounding structures without interference of other (monitoring) parties
  The first activity of the contractor is to make a plan for the monitoring activities
  In this plan, the contractor formulates the implementation of the monitoring specifications
  RPW checked and approved monitoring plan

## Slide 41: From risk management to monitoring
An important tool of risk management during the construction phase is technical monitoring
The construction activities were to be executed very close to the metro station:
  The probability of causing deformations to the existing metro station was very high
  The client’s main condition: unobstructed running of metro traffic in metro station
The monitoring specifications were focused on these risks

## Slide 42: Hazard warning levels
The monitoring specifications contained general statements and detailed requirements specified per monitoring parameter (e.g. vibrations, noise, groundwater, and deformations). Typical demands includes:
The parameter to be measured
The required measuring range of the measuring instrument
The required accuracy and frequency of measuring
The hazard warning levels
The way of communication
In order to make corrective actions effective, it is essential to compare the measured parameters with predefined hazard warning levels:
These levels form an important part of the monitoring specifications
The main criteria for the hazard warning levels were to assure the structural integrity of the station and safe operation of metro traffic
The hazard warning levels of the metro station are based on possible deformation of the underground station

## Slide 43: Monitoring results
A monitoring system is as good as the way data and signals are processed and interpreted:
  Attention is given to implementation and communication of the hazard warning levels
The monitoring system of the contractor fulfilled all contractual requirements
The on-line presentation and automatic warning system made it possible to guard the safety of the station during all construction activities and intervene when necessary
The graphical on-line representation of the results made it easy to interpret the results of the monitoring system and evaluate the effect of the construction activities on the station

## Slide 44: 9. Conclusions

## Slide 45: Conclusions (1)
This methodology is considered the modern-day recommendation from the tunneling industry for a “comprehensive tunnel risk management system”:
  It describes the stages of risk management throughout the entire project implementation (early design phase, tendering and contract negotiation phase & construction phase)
In phase 1, the responsibility to establishing a risk policy and carrying out risk assessment is the owner alone:
  To identify risk and candidate risk reduction measures as early as possible in the project development
In phase 2, the potential contractor has certain input to the tender regarding risk management, but the owner is still the primary responsible party:
  During tender evaluation, it provides an important contribution to: (1) the selection of the contractor; and (2) development of the final contract during the negotiations

## Slide 46: Conclusions (2)
In phase 3, the primary responsibility moves on to the contractor to establish a risk management system and to carry out effective risk management:
  The owner should supervise, inspect and participate in this work
  The owner should further continue to assess and mitigate risks not covered by the contractor
The risk management should be performed in an environment of good cooperation between the parties:
  To achieve this “partnering” may be a valuable tool
  The process of partnering may be formulated as an exercise in encouraging good communication between the parties

## Slide 47: Conclusions (3)
“Tunneling Risk Management” for underground metro projects can be considered as a formula for minimizing cost to the owner while maximizing profit for the contractor and encompasses joint planning and problem solving, scheduling, mitigation of delays and value engineering
Therefore, the process of “partnering” may be seen as a risk mitigation measure for the owner and the contractor

## Slide 48: THANK YOU FOR YOUR ATTENTION!